## GanttChart
Gantt Chart Template © 2006-2018 by Vertex42.com.
| Project Start Date | 2019-02-02 |  |  |  | Display Week | 12 | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24
[8 empty] | 2019-04-15 | [6 empty] | 2019-04-22 | [6 empty] | 2019-04-29 | [6 empty] | 2019-05-06 | [6 empty] | 2019-05-13 | [6 empty] | 2019-05-20 | [6 empty] | 2019-05-27 | [6 empty] | 2019-06-03 | [6 empty] | 2019-06-10 | [6 empty] | 2019-06-17 | [6 empty] | 2019-06-24 | [6 empty] | 2019-07-01 | [6 empty] | 2019-07-08
 | time axis 2019-04-15 to 2019-07-14
WBS | TASK |  | PREDECESSOR | START | END | DAYS | % DONE | time axis 2019-04-15 to 2019-07-14
1 | TMA01 |  |  | 2019-02-02 | 2019-03-12 |  | 36%
1.1 | Read the module website resources |  |  | 2019-02-02 | 2019-02-03 | 2 | 100%
1.2 | Find potential projects at work |  |  | 2019-02-04 | 2019-02-05 | 2 | 100%
1.3 | Preperation and Planning |  |  | 2019-02-06 | 2019-02-19 | 14 | 60%
1.3.1 | Working title |  |  | 2019-02-06 | 2019-02-06 | 1 | 100%
1.3.2 | Decription and scope |  |  | 2019-02-07 | 2019-02-08 | 2 | 100%
1.3.3 | Major Tasks and Subtasks |  |  | 2019-02-09 | 2019-02-10 | 2 | 100%
1.3.4 | Lifecycle Model and schedule |  |  | 2019-02-11 | 2019-02-15 | 5 | 0%
1.3.5 | Resources skills and methods |  |  | 2019-02-16 | 2019-02-19 | 4 | 0%
1.4 | Project Work Completed |  |  | 2019-02-20 | 2019-03-05 | 14 | 0%
1.4.1 | Information Sources |  |  | 2019-02-20 | 2019-02-22 | 3 | 0%
1.4.2 | Project Work |  |  | 2019-02-23 | 2019-03-05 | 11 | 0%
1.5 | Review and reflection |  |  | 2019-03-06 | 2019-03-11 | 6 | 0%
2 | TMA02 |  |  | 2019-03-12 | 2019-04-16 |  | 0%
2.1 | Preperation and Planning |  |  | 2019-03-12 | 2019-03-19 | 8 | 0%
2.1.1 | Title and scope |  |  | 2019-03-12 | 2019-03-13 | 2 | 0%
2.1.2 | Resources |  |  | 2019-03-14 | 2019-03-16 | 3 | 0%
2.1.3 | Future Plan |  |  | 2019-03-17 | 2019-03-19 | 3 | 0%
2.2 | Project Work Completed |  |  | 2019-03-20 | 2019-04-06 | 18 | 0%
2.2.1 | Information Sources |  |  | 2019-03-20 | 2019-03-23 | 4 | 0%
2.2.2 | Project Work |  |  | 2019-03-24 | 2019-03-29 | 6 | 0%
2.2.2.1 | First Iteration |  |  | 2019-03-30 | 2019-04-06 | 8 | 0%
2.3 | Review and reflection |  |  | 2019-04-07 | 2019-04-15 | 9 | 0%
2.3.1 | Ways of Working |  |  | 2019-04-07 | 2019-04-09 | 3 | 0%
2.3.2 | Evalulating project management |  |  | 2019-04-10 | 2019-04-12 | 3 | 0%
2.3.3 | Legal, social ethical and professional issues |  |  | 2019-04-13 | 2019-04-15 | 3 | 0%
3 | TMA03 |  |  | 2019-04-16 | 2019-07-09 |  | 0%
3.1 | Draft Project Report |  |  | 2019-04-16 | 2019-04-30 | 15 | 0%
3.1.1 | Problem Description |  |  | 2019-04-16 | 2019-04-20 | 5 | 0%
3.1.2 | Account of related literature |  |  | 2019-04-21 | 2019-04-25 | 5 | 0%
3.1.3 | Account of project work and its outcome |  |  | 2019-04-26 | 2019-04-30 | 5 | 0%
3.2 | Review |  |  | 2019-05-01 | 2019-05-16 | 16 | 0%
3.2.1 | Review of current stage of project work |  |  | 2019-05-01 | 2019-05-04 | 4 | 0%
3.2.2 | Review Project Management |  |  | 2019-05-05 | 2019-05-07 | 3 | 0%
3.2.3 | Assess risks to project completion |  |  | 2019-05-08 | 2019-05-11 | 4 | 0%
3.2.4 | Review of personal development |  |  | 2019-05-12 | 2019-05-16 | 5 | 0%
3.3 | Project Work |  |  | 2019-05-17 | 2019-07-09 | 54 | 0%
3.3.1 | Second Iteration |  |  | 2019-05-17 | 2019-06-12 | 27 | 0%
3.3.2 | Final Iteration |  |  | 2019-06-13 | 2019-07-09 | 27 | 0%
4 | EMA |  |  | 2019-07-10 | 2019-09-16 |  | 0%
4.1 | Final Report |  |  | 2019-07-10 | 2019-09-16 | 68 | 0%
4.1.1 | Project title |  |  | 2019-07-10 | 2019-07-12 | 3 | 0%
4.1.2 | Problem description |  |  | 2019-07-13 | 2019-07-20 | 8 | 0%
4.1.3 | Account of related literature |  |  | 2019-07-21 | 2019-07-28 | 8 | 0%
4.1.4 | Account of project work and its outcome |  |  | 2019-07-29 | 2019-08-15 | 18 | 0%
4.1.5 | Review of current stage of project work |  |  | 2019-08-16 | 2019-08-27 | 12 | 0%
4.1.6 | Review of project management |  |  | 2019-08-28 | 2019-09-02 | 6 | 0%
4.1.7 | Review of personal development |  |  | 2019-09-03 | 2019-09-10 | 8 | 0%
4.1.8 | Check and Submit EMA |  |  | 2019-09-11 | 2019-09-15 | 5 | 0%
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## TermsOfUse
Terms of Use
Gantt Chart Template, by Vertex42.com
https://www.vertex42.com/ExcelTemplates/excel-gantt-chart.html
© 2006-2018 Vertex42 LLC
This spreadsheet template, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
You may download the spreadsheet template, make archival copies, and customize the template only for your personal use or use within your company or organization and not for resale or public sharing.
You may not remove or alter any Vertex42 logo, trademark, copyright, disclaimer, brand, terms of use, attribution, or other proprietary notices or marks within the template.
The template and any file, document, or other work including or derived from the template may NOT be sold, distributed, published to an online gallery, hosted on a website, or placed on any server in a way that makes it available to the general public.
Limited Private Sharing and Other Allowed Uses: See the complete license agreement to learn more about how you may or may not use this template.
View the Complete License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html